## How to use
JobMatchAI Tracker - how to use
1. Tracker sheet: your day-to-day. Fill the Date column as you go.
2. Status column has a dropdown: Not Started / In Progress / Done / Skipped.
Cells auto-colour: green = Done, yellow = In Progress, grey = Skipped.
3. Use the Notes column for blockers, links (PRs, commits), or what you learned.
4. Dashboard sheet updates automatically - overall % and per-week % complete.
5. Daily Schedule sheet = the fixed clock-time template. Adjust start time to taste.
6. Orange rows in Tracker = MOCK interview slots (from Week 3).
7. Green rows = Day-7 weekly checkpoints (Definition of Done). Don't advance until green.
Rule: if a week slips, cut PROJECT scope first - never interview prep.
Rule (language front-load): if on Wk1 Day 3 you can't hand-write a fixture +
comprehension cold, add 2 more sprint days - earned by evidence, not booked ahead.

## Dashboard
JobMatchAI - Progress Dashboard
Overall
Total tasks
Done
In Progress
Not Started
Skipped
% Complete
By Week
Week | Total | Done | % Done
1
2
3
4
5
6

## Tracker
Week | Day | Date | Time | Block | Task | Status | Notes
WEEK 1 | Foundations & Automation - Python
1 | Day 1 (Py sprint) |  | 10:00-11:30 AM | Language (90m) | Py: types, collections, comprehensions, f-strings (hand-write, no AI) | Not Started
1 |  |  | 11:45 AM-1:45 PM | Project (120m) | Lang sprint: 5 small hand-written katas, no AI | Not Started
1 |  |  | 2:45-3:45 PM | Design (60m) | Design: test pyramid vs trophy for JobMatchAI | Not Started
1 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: two-sum, Kadane, running-sum | Not Started
1 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: LinkedIn Open-to-Work draft; list 20 targets | Not Started
1 | Day 2 (Py sprint) |  | 10:00-11:30 AM | Language (90m) | Py: functions, args/kwargs, errors, modules, type hints + mypy | Not Started
1 |  |  | 11:45 AM-1:45 PM | Project (120m) | Lang sprint: generators, decorators, context managers (hand-write) | Not Started
1 |  |  | 2:45-3:45 PM | Design (60m) | Design: POM, separation of concerns, fixtures | Not Started
1 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: reverse words, valid anagram, first-unique-char | Not Started
1 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: resume variant #1 (Architect-lean) | Not Started
1 | Day 3 (Py sprint) |  | 10:00-11:30 AM | Language (90m) | Py: PyTest deep - fixtures, parametrize, markers, conftest (tiny katas) | Not Started
1 |  |  | 11:45 AM-1:45 PM | Project (120m) | GATE: hand-write a fixture + a comprehension COLD (escalation check) | Not Started
1 |  |  | 2:45-3:45 PM | Design (60m) | Design: test-data management | Not Started
1 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: group anagrams, two-sum-map, freq counter | Not Started
1 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: resume variant #2 (Staff-SDET-lean) | Not Started
1 | Day 4 (project starts) |  | 10:00-11:30 AM | Language (90m) | Fluency: redo Day 1-3 snippets from memory | Not Started
1 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: scaffold repo; FastAPI health endpoint; docker-compose Postgres; DB schema (SQLModel) + migration | Not Started
1 |  |  | 2:45-3:45 PM | Design (60m) | Design: testing HTTP clients (mocking/VCR/contract) | Not Started
1 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: window sum size-k, longest substr no-repeat | Not Started
1 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: STAR #1 (automation ROI 96%) | Not Started
1 | Day 5 |  | 10:00-11:30 AM | Language (90m) | Py: async/await, httpx, logging, pydantic settings | Not Started
1 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: 1st job-source client fetch->normalize (VCR unit test); ingest->store + GET /jobs; API tests (TestClient) | Not Started
1 |  |  | 2:45-3:45 PM | Design (60m) | Design: UI E2E vs component | Not Started
1 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: valid palindrome, container-most-water | Not Started
1 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: STAR #2 (led UI dev team) | Not Started
1 | Day 6 |  | 10:00-11:30 AM | Language (90m) | Fluency: redo 2 snippets from memory | Not Started
1 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: minimal Vue list page wired to API; basic Playwright test; skeleton runs E2E; README start | Not Started
1 |  |  | 2:45-3:45 PM | Design (60m) | Design: say the JobMatchAI test strategy out loud (5 min) | Not Started
1 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: redo 3 problems cold | Not Started
1 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: STAR #3 (quality miss+fix); finalize both resumes | Not Started
1 | Day 7 |  |  | Checkpoint | Day 7 CHECKPOINT: skeleton E2E green - PyTest+Playwright green - 2 resumes - 3 STAR - REST | Not Started
WEEK 2 | Automation depth + Matching + CI/CD start - TypeScript
2 | Day 1 (TS sprint) |  | 10:00-11:30 AM | Language (90m) | TS: types, interfaces, generics, async/Promises, fetch (hand-write) | Not Started
2 |  |  | 11:45 AM-1:45 PM | Project (120m) | TS katas: 5 small snippets, no AI | Not Started
2 |  |  | 2:45-3:45 PM | Design (60m) | Design: testing non-deterministic output (invariants/metamorphic/golden set) | Not Started
2 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: valid parentheses, min-stack | Not Started
2 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: START - 3 apps; Open-to-Work ON | Not Started
2 | Day 2 (TS/PW sprint) |  | 10:00-11:30 AM | Language (90m) | TS: Playwright config, fixtures, locators, auto-wait | Not Started
2 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: expand UI tests (list/filter/detail) in TS | Not Started
2 |  |  | 2:45-3:45 PM | Design (60m) | Design: flakiness root causes | Not Started
2 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: queue-via-stacks, daily-temperatures | Not Started
2 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps; ping 3 referrals | Not Started
2 | Day 3 |  | 10:00-11:30 AM | Language (90m) | TS: consolidate via project code | Not Started
2 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: embeddings score (cosine) stored; LLM matching (1 Claude call -> {score,matched,missing,tips}) parse+store | Not Started
2 |  |  | 2:45-3:45 PM | Design (60m) | Design: LLM-as-judge / eval harness | Not Started
2 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: longest consecutive seq, intersection | Not Started
2 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps; STAR #4 (influence w/o authority) | Not Started
2 | Day 4 |  | 10:00-11:30 AM | Language (90m) | Consolidate Py + TS via project | Not Started
2 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: data-driven matching tests (parametrize) + metamorphic assertions | Not Started
2 |  |  | 2:45-3:45 PM | Design (60m) | Design: CI pipeline stages/gating/artifacts | Not Started
2 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: min-window-substring | Not Started
2 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps; STAR #5 (mentoring) | Not Started
2 | Day 5 |  | 10:00-11:30 AM | Language (90m) | Docker: Dockerfiles (Python + Node) | Not Started
2 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: dockerize FE+BE; compose full stack + LocalStack | Not Started
2 |  |  | 2:45-3:45 PM | Design (60m) | Design: containerized test envs | Not Started
2 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: subsets, permutations | Not Started
2 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps | Not Started
2 | Day 6 |  | 10:00-11:30 AM | Language (90m) | Review week's Py+TS | Not Started
2 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: first CI job (lint + PyTest + Playwright) GREEN | Not Started
2 |  |  | 2:45-3:45 PM | Design (60m) | Design: articulate CI strategy | Not Started
2 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: review week | Not Started
2 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: weekly review | Not Started
2 | Day 7 |  |  | Checkpoint | Day 7 CHECKPOINT: matching works - tests green in CI - 8+ apps - 5 STAR - REST | Not Started
WEEK 3 | CI/CD + Terraform + Java kata + first mocks - Java
3 | Day 1 |  | 10:00-11:30 AM | Language (90m) | Java: classes, collections, streams, Maven/Gradle | Not Started
3 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: Jenkinsfile stages (checkout->lint->unit->api->ui->report) | Not Started
3 |  |  | 2:45-3:45 PM | Design (60m) | Design: sysdesign 'framework for microservices at scale' | Not Started
3 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: tree inorder/level-order | Not Started
3 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 3 apps | Not Started
3 | Day 2 (MOCK) |  | 10:00-11:30 AM | Language (90m) | Java: RestAssured + TestNG setup | Not Started
3 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: port subset of API tests to RestAssured | Not Started
3 |  |  | 2:45-3:45 PM | Design (60m) | MOCK #1: framework design | Not Started
3 |  |  | 3:45-4:30 PM | DSA (45m) | Debrief mock: log gaps + feedback | Not Started
3 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps | Not Started
3 | Day 3 |  | 10:00-11:30 AM | Language (90m) | Java: finish RestAssured suite (assertions, data providers) | Not Started
3 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: HTML report + JUnit XML wired into pipeline | Not Started
3 |  |  | 2:45-3:45 PM | Design (60m) | Design: test-result reporting/observability | Not Started
3 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: max-depth, validate-BST | Not Started
3 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps; STAR #6 | Not Started
3 | Day 4 |  | 10:00-11:30 AM | Language (90m) | Consolidate Java | Not Started
3 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: Terraform basics; provision Postgres+SQS on LocalStack | Not Started
3 |  |  | 2:45-3:45 PM | Design (60m) | Design: IaC + ephemeral envs | Not Started
3 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: tree path-sum | Not Started
3 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps | Not Started
3 | Day 5 (MOCK) |  | 10:00-11:30 AM | Language (90m) | Review Java suite | Not Started
3 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: Terraform ECR+ECS/EKS skeleton; Jenkins build->push->deploy (dev) | Not Started
3 |  |  | 2:45-3:45 PM | Design (60m) | MOCK #2: live coding | Not Started
3 |  |  | 3:45-4:30 PM | DSA (45m) | Debrief mock: log gaps + feedback | Not Started
3 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps | Not Started
3 | Day 6 |  | 10:00-11:30 AM | Language (90m) | Review week | Not Started
3 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: pipeline E2E green incl. notify; tidy | Not Started
3 |  |  | 2:45-3:45 PM | Design (60m) | Design: articulate CI/CD + IaC story | Not Started
3 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: review | Not Started
3 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: weekly review | Not Started
3 | Day 7 |  |  | Checkpoint | Day 7 CHECKPOINT: pipeline deploys via Terraform - Java suite runs - 2 mocks - 8+ apps - REST | Not Started
WEEK 4 | Cloud/K8s + AWS runtime + mocks
4 | Day 1 |  | 10:00-11:30 AM | Language (90m) | Review / consolidate | Not Started
4 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: search->worker pushes to SQS; ingest pulls | Not Started
4 |  |  | 2:45-3:45 PM | Design (60m) | Design: idempotency / retries / DLQ | Not Started
4 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: grid BFS/DFS | Not Started
4 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 3 apps | Not Started
4 | Day 2 (MOCK) |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
4 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: scheduled trigger (EventBridge/ECS task or K8s CronJob) | Not Started
4 |  |  | 2:45-3:45 PM | Design (60m) | MOCK #3: system design | Not Started
4 |  |  | 3:45-4:30 PM | DSA (45m) | Debrief mock: log gaps + feedback | Not Started
4 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps | Not Started
4 | Day 3 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
4 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: deploy ECS/EKS to AWS dev via Terraform+Jenkins; ALB routing | Not Started
4 |  |  | 2:45-3:45 PM | Design (60m) | Design: ECS/K8s debugging (logs, describe) | Not Started
4 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: num-islands, clone-graph | Not Started
4 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps; STAR #7 | Not Started
4 | Day 4 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
4 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: resiliency - inject failures, verify retries/DLQ; worker PyTest | Not Started
4 |  |  | 2:45-3:45 PM | Design (60m) | Design: chaos/resiliency testing | Not Started
4 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: BFS shortest path | Not Started
4 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps | Not Started
4 | Day 5 (MOCK) |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
4 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: debug a broken pod/task live, fix | Not Started
4 |  |  | 2:45-3:45 PM | Design (60m) | MOCK #4: debugging + CI/CD deep-dive | Not Started
4 |  |  | 3:45-4:30 PM | DSA (45m) | Debrief mock: log gaps + feedback | Not Started
4 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: 2 apps | Not Started
4 | Day 6 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
4 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: harden deploy; secrets via Secrets Manager; docs | Not Started
4 |  |  | 2:45-3:45 PM | Design (60m) | Design: articulate cloud/runtime story | Not Started
4 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: review | Not Started
4 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: weekly review | Not Started
4 | Day 7 |  |  | Checkpoint | Day 7 CHECKPOINT: running in cluster - scheduled ingestion - resiliency proven - 2 mocks - REST | Not Started
WEEK 5 | Performance + Observability + live interviews
5 | Day 1 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
5 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: K6/JMeter on matching API; baseline p95/p99 | Not Started
5 |  |  | 2:45-3:45 PM | Design (60m) | Design: perf test strategy | Not Started
5 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: heap/top-k | Not Started
5 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: prioritize live interviews | Not Started
5 | Day 2 (MOCK) |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
5 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: instrument (Prometheus/CloudWatch + structured logs) | Not Started
5 |  |  | 2:45-3:45 PM | Design (60m) | MOCK #5: perf scenario | Not Started
5 |  |  | 3:45-4:30 PM | DSA (45m) | Debrief mock: log gaps + feedback | Not Started
5 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: live | Not Started
5 | Day 3 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
5 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: Grafana/CloudWatch dashboards (throughput, queue depth, latency, LLM cost) | Not Started
5 |  |  | 2:45-3:45 PM | Design (60m) | Design: observability-driven testing | Not Started
5 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: top-k, merge-intervals | Not Started
5 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: STAR #8 | Not Started
5 | Day 4 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
5 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: find bottleneck (LLM latency/cost, DB N+1) -> fix (cache/batch/index) -> re-measure | Not Started
5 |  |  | 2:45-3:45 PM | Design (60m) | Design: capacity/scaling | Not Started
5 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: review | Not Started
5 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: live | Not Started
5 | Day 5 (MOCK) |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
5 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: document perf tuning (before/after); add perf gate to CI | Not Started
5 |  |  | 2:45-3:45 PM | Design (60m) | MOCK #6: Principal leadership/behavioral | Not Started
5 |  |  | 3:45-4:30 PM | DSA (45m) | Debrief mock: log gaps + feedback | Not Started
5 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: live | Not Started
5 | Day 6 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
5 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: polish dashboards + perf README | Not Started
5 |  |  | 2:45-3:45 PM | Design (60m) | Design: articulate perf + observability story | Not Started
5 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: review | Not Started
5 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: weekly review | Not Started
5 | Day 7 |  |  | Checkpoint | Day 7 CHECKPOINT: load-tested - dashboards live - a documented fix - 2 mocks - REST | Not Started
WEEK 6 | AI-agentic testing + polish + close
6 | Day 1 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
6 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: worker->agent (Claude tool-use: search/fetch/score/save + loop) | Not Started
6 |  |  | 2:45-3:45 PM | Design (60m) | Design: agent architecture + guardrails | Not Started
6 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: light review | Not Started
6 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: interviews | Not Started
6 | Day 2 (MOCK) |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
6 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: agent reads JD -> generates test cases/data | Not Started
6 |  |  | 2:45-3:45 PM | Design (60m) | MOCK #7: Principal test vision/strategy | Not Started
6 |  |  | 3:45-4:30 PM | DSA (45m) | Debrief mock: log gaps + feedback | Not Started
6 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: interviews | Not Started
6 | Day 3 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
6 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: test the agents (eval harness, stub-LLM mocks, guardrail + cost/latency assertions) | Not Started
6 |  |  | 2:45-3:45 PM | Design (60m) | Design: testing AI systems | Not Started
6 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: light | Not Started
6 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: interviews | Not Started
6 | Day 4 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
6 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: end-to-end integration; close gaps | Not Started
6 |  |  | 2:45-3:45 PM | Design (60m) | Design: whole-system articulate | Not Started
6 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: light | Not Started
6 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: interviews | Not Started
6 | Day 5 (MOCK) |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
6 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: README + architecture diagram + 3-min demo video | Not Started
6 |  |  | 2:45-3:45 PM | Design (60m) | MOCK #8: full loop simulation | Not Started
6 |  |  | 3:45-4:30 PM | DSA (45m) | Debrief mock: log gaps + feedback | Not Started
6 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: offer/negotiation prep | Not Started
6 | Day 6 |  | 10:00-11:30 AM | Language (90m) | Review | Not Started
6 |  |  | 11:45 AM-1:45 PM | Project (120m) | Proj: final polish; pin repo; LinkedIn Featured | Not Started
6 |  |  | 2:45-3:45 PM | Design (60m) | Design: retro - list weak spots to keep drilling | Not Started
6 |  |  | 3:45-4:30 PM | DSA (45m) | DSA: light | Not Started
6 |  |  | 4:45-5:15 PM | Apply (30m) | Apply: continue until signed | Not Started
6 | Day 7 |  |  | Checkpoint | Day 7 CHECKPOINT: agent works - agents tested - demo recorded - portfolio public - CELEBRATE | Not Started

## Daily Schedule
Daily Time Template (~6 focused hrs, weekdays)
Time | Block | What
10:00-11:30 AM | Block 1 - Language (90m) | Hand-write code, NO AI. Language of the week.
11:30-11:45 AM | Break | Coffee / walk
11:45 AM-1:45 PM | Block 2 - Project (120m) | JobMatchAI - the week's slice + its tests.
1:45-2:45 PM | Lunch | Rest
2:45-3:45 PM | Block 3 - Design (60m) | Design/theory + 1 framework/system-design prompt.
3:45-4:30 PM | Block 4 - DSA (45m) | 2 problems, pattern of the day.
4:30-4:45 PM | Break | Reset
4:45-5:15 PM | Block 5 - Apply (30m) | Applications + STAR stories + LinkedIn.
MOCK days (Wk3+) | 2 days/week | Blocks 3-4 (2:45-4:30 PM) become a full MOCK INTERVIEW + debrief.